## Enhanced_Audit_Tracker(Audit Tr
ID | Category | Issue | Details | Action | Owner | Responsibility | Priority | Governance Checklist | Image/Marking
1 | Code Quality | Obj folders committed | Obj/bin folders found | Remove & update .gitignore | Developer | Dev (implement) / DevOps (enforce) | High | CI check to block obj/bin commits; PR review | Mark obj folders
2 | Code Quality | NuGet binaries committed | DLLs checked in | Remove binaries | Developer | Dev / DevOps | High | CI validation for binaries | Highlight binaries
3 | Repo Hygiene | Missing .gitignore | Ignore rules missing | Add standard .gitignore | Developer + DevOps | Dev (add) / DevOps (template) | High | Repo template with .gitignore
4 | Naming | Improper naming | Blazorcommon unclear | Rename properly | Developer | Dev | Medium | Code review naming standards
5 | Pipelines | Multiple pipelines | Duplicate pipelines | Consolidate | DevOps | DevOps | High | Single pipeline policy | Mark duplicates
6 | Pipelines | Invalid config | Missing paths | Fix YAML | DevOps | DevOps | High | Pipeline validation checks | Highlight missing paths
7 | Repo Hygiene | Empty classes | Empty files | Delete unused | Developer | Dev | Medium | PR review rule | Highlight files
8 | Branching | Too many branches | Abandoned branches | Cleanup | Developer | Dev / DevOps | High | Branch cleanup policy
9 | Branching | Pending PRs | PRs not merged | Complete/merge | Developer | Dev | High | PR tracking + SLA | Highlight PR list
10 | Process | No reviews | No 4-eye reviews | Enable policies | DevOps | DevOps | High | Mandatory reviewers policy
11 | Security | Secrets risk | Tokens/passwords | Enable scanning | DevOps | DevOps | Critical | Enable secret scanning in CI
12 | Consistency | Folder inconsistency | Structure varies | Standardize | Developer + DevOps | Dev (follow) / DevOps (define) | Medium | Repo structure guideline | Mark inconsistencies